# Staffing and Volunteers

Contents

Staffing and Volunteers	1

General Comments	2

Not having enough volunteers to make the event safe for attendees	3

Volunteers needing breaks during the event	3

Flourish Planning team/CYF team needing breaks during the event.	3

Volunteers behaving in an aggressive/abusive manner towards other attendees or volunteers	4

Volunteer uses discriminatory or other inappropriate language to another attendee/volunteer	5

Two or more volunteers get into a disagreement	6

Volunteer arrives under the influence of alcohol/drugs	6

Volunteer intrudes personal space which may include inappropriate touching.	6

## General Comments

All volunteers have been safely recruited to ‘Flourish’. All volunteers have completed a recruitment form, been issued with a role description, and have had 2 references collected, and as per the role descriptions DBS’s and safeguarding training checked.

The following role descriptions have been issued

- Chaplaincy Team

- Chief Steward

- Children’s Stream

- Safeguarding Officer

- Event Steward

- Set dressing and prayer spaces

- Host

- Photography

- Tech

- Youth Stream

A timetable will be created with Sue Southcoat alongside Naomi Prince to ensure that there are enough stewards active at a time, whilst also co-ordinating with sessions that they want to attend and Kairos.

| Possible risk | Likelihood of risk: low, medium or high | Impact or severity should risk occur: low, medium or high? | Action to be taken to reduce risk | Whose responsibility? |
| --- | --- | --- | --- | --- |
| ### Not having enough volunteers to make the event safe for attendees | Low Medium High | Low Medium High | - Decide minimum number of volunteers required for safe event (if Children and Young people are involved, ratios may need to be considered) - Ensure that there is a rota for volunteers so that everyone is clear when they are expected to help out - Ensure all volunteers know who to telephone if they are unwell or unable to attend - After the event, follow up with absent volunteers. | - Flourish Planning team and CYF planning team to decide minimum safe numbers for operation Ideally 50 stewards within the main programme Check with CYF lead about minimum for CY stream - Volunteers to be given rota and all to be made aware who to contact if they are unwell or unable to attend |
| ### Volunteers needing breaks during the event | Low Medium High | Low Medium High | - To liaise with other members of the volunteer team so that there are always a suitable number of volunteers for each activity. - To create a rota to ensure that there are regular breaks | - Sue Southcoat/Naomi/Lois to provide a way for volunteers to indicate when they need a break - Sue Southcoat/Naomi Prince to create a rota and share this with the volunteers - Find suitable way to communicate with stewards during the event. |
| ### Flourish Planning team/CYF team needing breaks during the event. | Low Medium High | Low Medium High | -Highlight periods of the day where team may not be urgently required and encourage breaks to be taken. -Room with drinks and food will be available to team throughout the weekend | - Chaplaincy Team to encourage and enable breaks to be taken throughout the weekend. |
| ### Volunteers behaving in an aggressive/abusive manner towards other attendees or volunteers | Low Medium High | Low Medium High | - Volunteer will be asked kindly and politely to stop the behaviour, leave the argument/disagreement and come away to discuss the issue quietly with Naomi Prince and Sue Southcoat. - anyone who becomes a focus of the individual is to be protected and withdrawn from harm. The abusive volunteer should be accompanied at all times until they calm down or are removed as appropriate - If individual does not comply with what is requested, they would politely be asked to leave premises - If volunteer continues to be disruptive and will not leave, attendee should be notified that Police will be called to remove them - report situation to ROS - If there is an immediate risk of harm to themselves, others or property, Police may need to be called, and ROS informed of action. | - All teams to share responsibility for observing behaviour of other volunteers for any problems -Event Safeguarding Team will be informed as appropriate. - Naomi Prince will make decisions relating to whether a attendee should be asked to leave |
| ### Volunteer uses discriminatory or other inappropriate language to another attendee/volunteer | Low Medium High | Low Medium High | - Volunteer to be taken aside by Naomi Prince or other appropriate person to explain why the language they used is not acceptable. - Naomi, Leslie or another appropriate person to ask them to step down as a volunteer but explain that they are welcome to stay at the event as long as there is no repetition of behaviour. - Chaplaincy team to ensure victim of the discrimination has someone to speak to and is OK. Explain that the volunteer will be managed appropriately. - Report incident to ROS - If there is an immediate risk of harm to themselves, others or property, Police may need to be called, and ROS informed of action. | - Naomi Prince/Sue Southcoat to speak to the Volunteer - Chaplaincy team to speak to the victim and ensure that they are okay - Naomi Prince to report incident to ROS |
| ### Two or more volunteers get into a disagreement | Low Medium High | Low Medium High | - Volunteers will be politely asked to stop the behaviour and if necessary each given a different member of the chaplaincy team to speak to about the situation and deescalate the situation. -If volunteers do not comply and continue to argue with each other, Sue Southcoat and Naomi Prince reassess the rota and explore ways of resolution. - Report incident to ROS - If there is an immediate risk of harm to themselves, others or property, Police may need to be called, and ROS informed of action. | -Sue Southcoat and Naomi Prince to be involved and ensure each individual gets appropriate pastoral support. Naomi Prince to report incident to ROS |
| ### Volunteer arrives under the influence of alcohol/drugs | Low Medium High | Low Medium High | - If their behaviour changes or they become disruptive or inappropriate they will be politely asked to leave the event. -If situation severe, consider reporting incident to ROS. | - All volunteers to share responsibility for observing behaviour of fellow volunteers for problems. -Naomi Prince or other appropriate person will make decisions relating to whether a volunteer should be asked to leave. |
| ### Volunteer intrudes personal space which may include inappropriate touching. | Low Medium High | Low Medium High | All volunteers will receive a summary document which will include guidance on ensuring respect for personal space. | Naomi to create summary document for volunteers reiterating key expectations |